## Slide 1: Implement project governance

## Slide 2: Agenda
  Discuss the Solution Architect’s role in project governance
  Discuss techniques for keeping a project on track
  Explore scenarios that could cause a project to fail
Notes: The solution architect for Microsoft Power Platform has a key role on a project. Typically, the solution architect will implement governance, change processes, and monitor the project progress. This learning path explains the role of the solution architect in implementing project governance.
This is a discussion heavy session
Note: If you have experienced students, you can decide to skip some of the slides and focus on discussions
Timing: This learning path takes 30 minutes plus 20 minutes for the exercise

## Slide 3: Microsoft Learn module
Solution Architect series: Implement project governance for Power Platform and Dynamics 365
https://learn.microsoft.com/training/modules/project-governannce/
Notes: Link to student courseware on Learn
Solution Architect series: Implement project governance for Power Platform and Dynamics 365
https://learn.microsoft.com/training/modules/project-governannce/

## Slide 4: Keeping a project on track is easy, how do we do it?
Notes: Classroom discussion
Sure sounds easy, what are the classes ideas on how the solution architect can help keep a project on track. Use these ideas to pair up with the rest of the module discussion
Consider the projects that you've worked on as a project team member and then answer these questions:
Did the project have a governance process?
If a governance process was established, was it followed?
Were risks documented and mitigated?
Was a change control process established?
How effective were these processes and could they have been improved?

## Slide 5: Solution Architect can help by…
  Being a key member of the governance team
  Help manage changes in scope and requirements
  Look out for issues in the requirements including regulatory, compliance, auditing, and security
  Not over-promising and helping to encourage small steps towards a big goal
Notes: During the project the solution architect is a key member of a governance team. As scope or requirements change they are typically involved in review and impact assessment and are on the front lines for allowing scope creep to happen and to prevent it from happening. You may not have a seat at the governance table, but your impact will always be there.

## Slide 6: Any process is better than no process!
  Often customers will have their own governance process
  Governance should be inline with contractual terms for changes agreed to by customer
  If no process is in place, the Solution Architect should push for creation
Notes: Even a sticky note is better than nothing…It’s ok to mix and match in order to fill in the missing pieces of a customers process
Most the time customer will have their own and you will either adopt theirs or build a hybrid

## Slide 7: Recipes for failure
  Not documenting assumptions
  Not doing risk management
  Over-promising
  Designing with incorrect assumptions or requirements
  Other thoughts?
Notes: These are just some of the common areas of failure, what does the group think others are? Discuss…
Others
Organization politics
Not having buy in from senior management
Not being able to have an enterprise vision
plus
Not documenting decisions
No change management
Unrealistic customer expectations

## Slide 8: Recipes for success
  Know what done looks like, from your customer’s perspective not yours
  Project checkpoints – How are we doing?
  Be more agile, retrospectives, lessons learned
  Have a change control board to manage change

## Slide 9: How are we doing?
Insist in a way to measure how things are going
Example, Red, Yellow, Green
Notes: This is from the Sure Step project status document, it highlights the Red, Yellow Green concept. It provides a quick glance visual health of the project and what shape the areas are in. Good teams raise issues early, mitigate the issue, and escalate to red without last minute surprise.
This exact method doesn’t have to be used, but you should agree on a simple health check process

## Slide 10: How did we do?
  Establish checkpoints to look back at progress
  Push for no fault discussions
  Turn failures into goals for next checkpoint review
  How did your customer think you did?
  Look inside and outside your project team for feedback.

## Slide 11: Providing reviews and feedback
Notes: Solution architect role is to provide reviews and feedback to team members
Keeping on track with actionable feedback – see next slide

## Slide 12: Keeping on track with actionable feedback
  Bad news does not get better with time- SPEAK UP EARLY!
  Provide feedback to others to help shape the solution
  Feedback can be to project team or customer
  This can happen as early as the RFP/SOW creation and ongoing throughout the project
  Responsible for keeping feedback constructive and actionable
Notes: Respect the client chain of command but be prepared to shake things up if needed.
Work on your communication skills, don’t be too rough, don’t be too gentle.

## Slide 13: Sharing bad news
Notes: Classroom discussion
Instructor- this is a discussion slide. Have the students work on how to share bad news.
Occasionally, the solution architect provides feedback about an issue that might not be well-received. Bad news does not improve with time. The solution architect must acknowledge and share bad news early in the process.
Use your own examples, or offer some of these:
The cost of user licenses will increase by 87% if we move ahead with that requirement as written.
That feature set is being deprecated.
With the added relationship the data import will now take 312 days.

## Slide 14: Keep it actionable
“Something is amiss here”
  No clear call to action, team member is left trying to figure out what the problem is
“Confirm that setting “X” in Microsoft docs I think it might be wrong”
  Clear problem statement and place to look
Notes: The solution architect needs to ensure that feedback, especially bad news, is actionable. Stating that "Something is amiss" is pointless because it provides no clear call to action and the recipient is left trying to figure out what the issue might be. Instead, the solution architect should construct a clear problem statement and then provide references and the potential impact on the project.

## Slide 15: Help people reach the same conclusion
  “That won’t work” – likely to put someone on the defensive
  “Will that cause 1,000,000 Power Automate flows to be running with that configuration?”
  Highlights your concern but encourages them to think through and resolve the concern
  Avoid saying “No”; offer options instead, negotiate requirements
Notes: Though the solution architect might have the most expertise, you need to help the project team members and customer reach the resolution to an issue. Stating, "That won’t work" will likely cause someone to feel defensive. The solution architect should always be constructive and avoid saying "No" too often. Instead, offer options or negotiate the requirements.

## Slide 16: Fine line between review and do the work
  You don’t have to solve every problem
  Give it back with suggestions on where to look for answers
  Encourage POC or other tests to validate where it’s not clear a solid solution is proposed

## Slide 17: Working as a team
Notes: The solution architect will generally be the most experienced person on a project and might be the most skilled in many tasks in a project. However, a solution architect can't do everything alone. The solution architect needs to break down the work and delegate it to the most appropriate team member.
Essentially, the solution architect owns the overall vision of the project's technical solution and needs to communicate that vision to the team.

## Slide 18: Solution Architect helps here by…
  Own the overall vision of the technical solution and communicate it to the team
  Role model and mentor other team members
  Solution Architect will establish the breakdown that will be used for the functional and technical design

## Slide 19: Not everyone on a team is a rock star
  You can’t do everything alone
  Solution Architect is often responsible for setting the example and mentoring others
  You don’t always get to choose your team
  Learn how to assess skills of team…and weaknesses
Notes: Often you won’t get to pick your full team, and will have to work with what you are assigned

## Slide 20: Assessing your team’s skills
You don’t have to ask for a resume to learn how much Microsoft Power Platform they know
Have a set of probing ‘discussion’ questions to test knowledge
    e.g., Managed vs Unmanaged solutions
    e.g., Business rule vs. Power Automate cloud flow
Small assignments, assess results
Encourage them to explain a proposed solution, assess the results
Develop your own skills matrix as the project evolves, leverage strengths of team to succeed

## Slide 21: Are you a good example?
  Solution Architect often looked to as the leader
  Solution Architect often sets the tone for the rest of the team
  “Oh, we don’t need to do that it’s a waste of time”
Notes: Sure the engagement manager and project manager lead the project, but often times the SA is looked at as the “real” leader and can set the tone and pace for how the team works

## Slide 22: Staying on the same page
  Solution Architects often bring to the table a lot prior knowledge and experience
  You also often get to see the “Big Picture”
  Don’t assume everyone else has the same
  Assumptions and generalizations can be risky
  Increased, clear communication can help

## Slide 23: Tips for Breaking down the design work
  Look for logical functionality in the application
  Customer Service
  Customer Acquisition
  Looking at horizontal solution features
  Document Management
  Computer Telephony Integration (CTI )

## Slide 24: Establishing standards for the team
  Consistency across customizations
  Consistency across software extensions
  Consistency across the user experience
  Some things in the Microsoft Power Platform that are hard to change later
  Schema prefix
  Table or Column Names
Notes: Having a 1-3 page document you give new team members is ideal

## Slide 25: Team working environments
  Multiple people working on the project some may be co-located or dispersed remotely
  Development environment topology needs to be determined
  Some type of testing environment(s) will be needed
  Microsoft Power Platform does not provide version-controlled tracking by default
Notes: We cover ALM in its own module later in the course

## Slide 26: What else can the Solution Architect do to help teams work better together?
Notes: Classroom discussion

## Slide 27: Group exercise: Review work
During this exercise, you will be reviewing the project workbook for the Contoso project created by another team of Solution Architects. Part of this exercise is deciding how best to manage your time. Make sure you find out from your instructor the time allotted.
Review Project Workbook Details and Prepare Feedback
Share feedback with other teams
Notes: Exercise can be found here on GitHub
https://github.com/MicrosoftLearning/PL-600-Microsoft-Power-Platform-Solution-Architect/blob/master/Instructions/Exercises/Exercise03%5BPL-600%5D_Review_work.md
Timing: 20 minutes
Note: In a virtual delivery the instructor can decide to point out key findings rather than have student’s review each team’s work.

## Slide 28: Check your knowledge

## Slide 29: Check your knowledge
Implement Project governance
Learning Path 3
Use your PC or mobile device
Go to (insert polling app link of your choice)
Enter code: 123-45-678
Please participate
Which one?
A). None
B). A little
C). Lots
Notes: Microsoft Learning recommends using polling to be completed for every 7 – 10 slides and preferably at the end of each section. This helps break classes up and adds more interactivity especially for remote classes.
In order to promote interactivity, WWL suggests the use of Mentimeter, Kahoot or a similar polling technology. Please feel free to adjust this slide as needed and populate with the instructions based on the polling tool of your choice.
Learn note:
Learn has Knowledge checks individually through the Learn modules
https://learn.microsoft.com/en-us/training/modules/project-governannce/6-check

## Slide 30: Check your knowledge
Which one of the following statements is true regarding feedback?
Feedback must always be positive.
Feedback should be left until project checkpoints.
Feedback must always be constructive.
Feedback is provided only to team members.
Answer=C
Solution
Notes: Feedback must be actionable with a clear statement of the problem and suggestions of what to do or where to look.

## Slide 31: Check your knowledge
How should a solution architect assess the skills of the team?
Require team members to be certified in Power Platform.
Review the resumes of each team member.
Ask team members to complete a test of questions about customizing Power Platform.
Ask each team member probing questions.
Answer=D
Solution
Notes: A solution architect should have a set of probing discussion questions that can be asked to test each team member's knowledge.

## Slide 32: Summary
  Business application projects are a team effort requiring coordination and planning to succeed
  Solution Architects are often the glue that holds a team together
  Reviewing others work is an essential part of the Solution Architect’s Role on the project
  Up front actionable feedback will result in less headaches as the project progresses

## Slide 33: Closing slide